Sir Alexander Fleming Pupil Premium Strategy 2020-2021

At Sir Alexander Fleming Primary School and Nursery, we instil in all our children that anything is possible if they work hard and have a positive attitude. As leaders and teachers, it is within our remit to look after our disadvantaged children and treat them like VIPs in their school environment; our aspirations for them are as equally high as non-disadvantaged. 
We ensure that no child falls through the net and we take a great deal of care to ensure they are socially and emotionally taken care of. We believe in high quality pastoral care and our team treat all children like their own. We create a sense of belonging and a connection to Sir Alexander Fleming and this is the best measure of success.

| School Context |  |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- | --- |
| Total number of pupils eligible for pupil premium funding | Number of eligible girls | Number of eligible boys | Number of pupils eligible for free school meals in the last six years (ever 6 FSM) | Number of looked after children (LAC) | Number of post LAC | Number of service children |
| 209 / 388 | 100 | 109 | 225 | 5 | 0 | 6 |

| - Current Attainment for Disadvantaged Children Internal data from End of Spring term 2020 (COVID-19) |  |  |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- | --- | --- |
|  | Reception 28 | Year 1 31 | Year 2 35 | Year 3 35 | Year 4 29 | Year 5 21 | Year 6 33 |
| % achieving ARE or above in maths | 54% | 64% | 68% | 60% | 66% | 77% | 69% |
| % achieving ARE or above in reading | 54% | 62% | 60% | 54% | 51% | 66% | 66% |
| % achieving ARE or above in writing | 54% | 68% | 66% | 58% | 65% | 67% | 82% |
| % achieving GD in maths | 18% | 16% | 17% | 11% | 21% | 29% | 30% |
| % achieving GD in reading | 22% | 10% | 9% | 11% | 10% | 33% | 24% |
| % achieving GD in writing | 22% | 3% | 17% | 9% | 17% | 19% | 24% |

| - Barriers to future attainment for PPG pupils |  |  |
| --- | --- | --- |
| - In-school barriers (issues to be addressed within school) |  | - External barriers (issues which require out of school assistance) |
| - Coupled vulnerability with SEND is an issue for our PP eligible pupils. - Mobility in from other settings – pupils who are PP eligible join us often lower than the expectations of their peers. - Home learning environments, such as parental engagement and home support may have a detrimental effect on PP pupils. - Impact of COVID-19 and non-school attendance – lack of home learning / stimulation at home / impact of Adverse Childhood Experiences (mental health, drug misuse, lack of money, hunger, domestic violence) |  | - Disadvantaged pupils are less likely to participate in school visits/ residentials / sporting activity, without significant support from school staff. - Disadvantaged pupils are less likely to have the appropriate equipment for school (uniform, shoes, PE Kit, Forest School kit, coats) |
| - Desired outcomes Success Criteria |  |  |
| More disadvantaged pupils achieve age related expectations at the end of KS1 and KS2 in Reading, Writing and Maths | A higher number of disadvantaged eligible pupils will achieve Age Related Expectations / Greater Depth Standard in individual subjects and as a combined measure. Internal data / teacher assessment termly End of Key Stage judgements and STAT assessments will be used to make the judgements, supported by in school moderation and testing (if happening) |  |
| Disadvantaged pupils are not disadvantaged by low attendance | Gap diminishing and disadvantaged children maintain attendance of at least 95%. Gap between disadvantaged and non-disadvantaged peers to narrow. This will be inline with national levels of attendance. Monitored by Attendance Support and HT |  |
| Ensuring that our disadvantaged children are secure in their social and emotional fundamental skills | Disadvantaged eligible pupils will have received all the social and emotional support that they need to break down the barriers present to learning Children are resilient and show a positive attitude to learning |  |
| Ensuring that children are able to manage their own self-regulation strategies, from Nursery to Year 6 | Disadvantaged eligible pupils will be resilient and able to manage their own learning. This target links to the one above. |  |

Pupil Premium Objectives 2020-2021

| Pupil Premium Objectives for 2020-2021 academic year | Total Pupil Premium Allocation for 2020/2021 academic year: £314,441 |
| --- | --- |
| 1. Increase the % of Disadvantaged pupils attaining at Age Related expectations in Key Stage 1 and 2 Reading, Writing and Maths 2. A higher % of Disadvantaged children achieving Greater Depth in Reading, Writing and Maths therefore receiving more challenge within the classroom 3. PPG pupils are not disadvantaged by low attendance. 4. Ensure all disadvantaged pupils are provided with excellent pastoral care and provided with fair access to the wider curriculum 5. Disadvantaged pupils are less likely to have the appropriate equipment for school (uniform, shoes, PE Kit, Forest School kit) |  |

| - Planned Expenditure for 2020-2021 |  |  |  |  |
| --- | --- | --- | --- | --- |
| Objective 1: Increase the % of Disadvantaged pupils attaining at Age Related expectations in all year groups Reading, Writing and Maths Objective 2: Increase the % of Disadvantaged pupils attaining Greater Depth in all year groups therefore receiving more challenge within the classroom |  |  |  |  |
| Actions | Success Criteria | Timescales | Staff Lead | Monitored by |
| Create a PPG Team within school to monitor the progress of all disadvantaged children each term | Pupil voice Rigorously track data and identify any ‘gaps’ Review and rewrite PPG plan termly Be part of lesson observations with English and Maths with a focus of the Disadvantaged children | Termly | KT, LP | KT and PP Governor |
| CPD throughout the year, led by a range of advisors and school staff. | CPD evaluations will be undertaken, along with intervention observations proving the impact of the small group tuition upon the pupils. | Termly | SLT, TLR leads | KT and PP Governor |
| Small group/ 1:1 tuition to boost the attainment of pupils in KS2 led by an experienced teacher | KS2 groups identified by class teachers to work in small groups with an experienced teacher Half termly pupil progress meetings will track the difference between the pupil groupings and progress | 2.5 days a week | PG | KT and class teacher |
| SLT/ TLRs to monitor Quality First Teaching of all year groups during planned lesson observations | SLT / TLR leads/SENDCo will carry out book looks for the pupils who have received intervention. | Termly for English and Maths | Reading team Writing team Maths team | KT and PP Governor |
| SENDCO to monitor SEND / PP children and observe teaching. | Additional teaching assistants to support in cohorts where percentage of Disadvantaged / SEND pupils is at its highest SENDCo to monitor the quality of TA sessions – give feedback | Organised in September Half termly | LP | CK, KT and PP Governor |
| What is the evidence and rationale for this choice? Small group tuition is defined as one teacher or professional educator working with two, three, four, or five pupils. This arrangement enables the teacher to focus exclusively on a small number of learners. Intensive tuition in small groups is often provided to support lower attaining learners or those who are falling behind, but it can also be used as a more general strategy to ensure effective progress, or to teach challenging topics or skills. This can add 4+ months onto the progress of children. EEF foundation 2018 https://educationendowmentfoundation.org.uk/evidence-summaries/teaching-learning-toolkit/small-group-tuition/ One to one tuition is where a teacher, teaching assistant or other adult gives a pupil intensive individual support. It may be undertaken outside of normal lessons as additional teaching, for example as part of extending school time or summer schools, or as a replacement for other lessons by withdrawing the pupil for extra teaching. Evidence indicates that one to one tuition can be effective, on average accelerating learning by approximately five additional months’ progress. EEF foundation 2018 https://educationendowmentfoundation.org.uk/evidence-summaries/teaching-learning-toolkit/one-to-one-tuition |  |  |  |  |

| Objective 3: PPG pupils are not disadvantaged by low attendance |  |  |  |  |
| --- | --- | --- | --- | --- |
| Actions | Success Criteria | Timescales | Staff Lead | Monitored by |
| Behaviour Mentor project to begin for the next academic year, led by SLT And organised with TAs | SLT / HT to organise in September 2020 TA meetings Agenda item at meetings | Every 3 weeks | SLT SENDCO | KT and PP Governor |
| EWO funding to carry on and target the pupils where attendance is an issue and support these families in raising their attendance. | Attendance Review meeting Attendance Action Plan to be completed Individual action plans to be created for persistently absent children Attendance Support to track attendance, absentees and lates Analysis of attendance reports to drive actions and reflection of what has worked well, amending as is necessary. Incentives to encourage attendance / arrival on time Attendance Review panel with parents | Every 3 weeks | EWO HT Admin | KT and PP Governor |
| Nurture group to run to target the disadvantaged pupils who are identified as requiring additional support in KS1 and KS2 | SLT to monitor behaviour logs of key children and these will show a reduction in incidents Individual tracking of these children will see an impact on their attitudes towards learning and behaviour. Nurture groups identified with teachers, SENDCo and SLT Nurture groups to be closely monitored by SENDCo – attainment gaps for R, W, Ma | Every half term | Nurture team Deputy Head SLT SENDCo | KT and PP Governor |
| Subsidised after school sporting places available to all disadvantaged pupils across all key stages. | HT to monitor % of Disadvantaged pupils attending. Sports coaches to invite all children to participate in sport at all times, both in school and extracurricular. PE lead to analyse the numbers and % of disadvantaged eligible pupils who are attending after school clubs. | Every half term | PE coaches RB | KT and PP Governor |
| Increased Breakfast Club provision with reduced rates for PPG pupils | Head to monitor attendance of children % of PP children who attend | Every half term | Head | KT and PP Governor |
| What is the evidence and rationale for this choice? Many of our PP children experience barriers to their learning, which affect their self-esteem, which in turn effects their attitude towards their own learning. Our key worker project aims to give these children an adult champion in school who they can talk to, turn to for help and be a positive role model. These adults become a ‘parent’ in school, providing support for the most vulnerable where needed. Many of our PP eligible children find attending school or being on time for school hard. Attendance at school is crucial for these children to get the support that they need through quality first teaching and targeted interventions. Subsidised breakfast school places available for families who are struggling with attendance. Pastoral team are integral to the success of our PP pupils, both academically and social/ emotionally. We need our Pastoral team to remain as is currently, with additional support provided as and when necessary. Nurture club to be ran for all children, including PP eligible pupils, as nominated by CTs. Interventions which target social and emotional learning (SEL) seek to improve pupils interaction with others and self-management of emotions, rather than focusing directly on the academic or cognitive elements of learning. This can add 4+ months to a child’s progress https://educationendowmentfoundation.org.uk/evidence-summaries/teaching-learning-toolkit/socialandemotionallearning/ Sport is key to raising the self-esteem of many of our pupils. Pupils are invited to join lunchtime clubs, as well as after school clubs. No child is turned away from a club under any circumstances due to vulnerability. This can add 2+ months progress. https://educationendowmentfoundation.org.uk/evidence-summaries/teaching-learning-toolkit/sports participation/ |  |  |  |  |

| Objective 4: Ensure all disadvantaged pupils are provided with excellent pastoral care and provided with fair access to the wider curriculum |  |  |  |  |
| --- | --- | --- | --- | --- |
| Actions | Success Criteria | Timescales | Staff Lead | Monitored by |
| Ensure all curriculum and non-curriculum activities and visits are fully or part-funded so PP students are not disadvantaged | Students attend trips, visits and activities Payment plans are setup with parents Some visits will be subsidised | Annually | KT / Admin | KT and PP Governor |
| Ensure all pastoral leads / KS Managers / teachers / TAs have a keen focus on the PP students within their year group. | PP students feel well supported pastorally. Evidenced via student interviews /pupil voice | Ongoing | KT | KT and PP Governor |
| SLT mentoring of year groups targeted at PP and linked to behaviour | Mentored students improve progress Reduced FTE / behaviour letters / report cards | Ongoing Reviewed in SLT Meetings | CK | KT and PP Governor |
| Nurture provision to address the social and emotional needs of the children in KS1 and KS2. | Review how children return to school following COVID-19 – impact on behaviour, attitudes to learning Set up new Nurture groups / routines in KS1 and KS2 – discuss with SLT Create Lunchtime Club in ‘Open Learning Area’ for children who are unable to positively access the playground | First 8 days Week 3 Autumn term Autumn 1 | LP / JR / SLT LP / JR JM /TA | KT KT / SLT KT |

| Objective 5: Disadvantaged pupils are less likely to have the appropriate equipment for school (uniform, shoes, PE Kit, Forest School kit) |  |  |  |  |
| --- | --- | --- | --- | --- |
| Actions | Success Criteria | Timescales | Staff Lead | Monitored by |
| All children will have the appropriate equipment for school activities – PE kit, Forest School kit, shoes | Children will have a sense of belonging and will be prepared for all learning opportunities and experiences. School has a supply of PE kits purchased by FOS and children without kits have their own provided. FOS have purchased wet weather Forest School clothing for children School has a collection of school shoes to support families in need. Uniform can be purchased from the office and a payment plan can be provided (we do not supply free uniform to disadvantaged families) Non-branded uniforms are acceptable. | Ongoing | Inclusion team Admin FOS | KT |
| What is the evidence and rationale for this choice? School uniform is the clothing pupils are required to wear at school. There is a general belief in many countries that school uniform supports the development of a whole school ethos and therefore supports discipline and motivation. Evidence indicates that providing school uniform does not improve learning but can successfully build a sense of belonging and a development of ethos EEF foundation 2018 |  |  |  |  |

Sir Alexander Fleming Primary School

Pupil Premium Planned Expenditure for 2020-2021

| Area | Actions | £314,441 Cost | Evidence |
| --- | --- | --- | --- |
| Additional support across all phases | - Additional TAs assigned to every class (12) - 1:1 support for SEND / Disadvantaged children (2) - Additional targeted support for reading groups across KS1 | £144,000 £24,000 £6,000 | Data tracking – termly Monitoring file – lesson observations / book scrutiny / learning walk Assessment file – Workgroup – PPM Engagement of children – Pupil Voice Feedback from TAs |
| Small group tuition by qualified teacher | - Targeted action plans and strategic teaching to close any attainment gaps for identified groups in KS2 | £22,000 | Data tracking – termly Monitoring file – lesson observations / book scrutiny / learning walk Assessment file – Workgroup – PPM |
| Inclusion | - External agencies to support vulnerable children – Impact counselling / consultancy - Experienced Qualified teacher to lead KS2 Nurture provision - Behaviour Support Team to work with vulnerable children across school – CP/CIN/TAF/TAC in Nurture settings - Attendance Support Officer – full time in school - Nurture group – cost for additional TA support | £10,000 £38,690 £17,000 £17,000 £24,000 | Reduction in FTE Less behaviour incidents in class and on the playground Attendance figures Boxall profiles Data tracking |
| Pastoral teacher | - Scale 4 TA to work 5 days a week to work with children with social / emotional needs in a pastoral role | £17,000 | Reduction in FTE Less behaviour incidents in class and on the playground Data tracking |
| Multicultural Development Team | - Bilingual qualified teachers working with targeted EAL pupils – assessment and support for pupils / school | £2,240 | Data tracking of EAL, PPG children |
| School clubs | - Weekly 0.5 art / craft sessions / after school club (external teacher) - Daily lunchtime clubs – KS1 / KS2 run by support staff | £1,500 £1,500 | Discussions with children |
| Revision Guides for Year 6 children | - Support Revision guides for year 6 | £900 | All Year 6 children fully equipped for revision Emotional well-being of children supported by being resourced |
| School Uniform / Sports Kits | - School uniform and shoes for children - PE Kits - Trainers | £2,000 | Engagement Mental health and well-being of children Social skills improved Participation in PE – children are fully equipped for PE |
| External Visitors | - External visitors – theatre groups /music groups and teaching | £5,000 | Enjoyment and engagement Enrichment of education Life experiences |
| Forest School Provision | - EYFS forest school outdoor clothing / waterproof clothing and wellington boots | £500 | Enjoyment and engagement Enrichment of education Life experiences |
| Subsidise school visits | - Subsidises educational trips / visits / coaches - Arthog Activity week – clothing / Arthog Outreach provision for pupils | £10,000 | Enjoyment and engagement Enrichment of education Life experiences |
| Additional provision | - Breakfast club provision for vulnerable families/children – 2 support staff - Daily provision of toast for all children – cost of adult to prepare | £1,000 £500 | Attendance figures Children’s engagement |
| TOTAL PLANNED EXPENDITURE |  | £341,830 | Overspend of: £27,389 |